## Legend
Macrophage block course FS 2027: schedule template
Built by tools/schedule/gantt_build.py on 2026-10-28. Hand edits are fine, but a rebuild overwrites the Overview and the week sheets; lasting changes go into the script. After editing, run tools/schedule/gantt2readme.py.
Colour | Activity block
PLENARY | Plenary, lecture, debrief (fixed)
FACILITY | Facility slot: cytometer, facility lecture (fixed, reserved)
EXP1 | Wet lab Exp 1: polarize and characterize (plate with the polarizer, harvest, stain, acquire)
EXP3 | Wet lab Exp 3: polarize and challenge (plate, stimulate, harvest, ELISA)
DRY | Dry lab and desk work: setup, analysis, planning
POSTER | Poster and writing: introduction, significance, figures
EXT | Extension / nerd factor (group's choice)
BUFFER | Buffer / free
How to read it | One sheet per week: one column per day, one row per hour, 08:00 to 17:00 (Tuesdays from 13:00; Monday and Tuesday morning are the students' other lectures). Every full day opens with a self-study hour. Below the hour grid: a staff row and a resources row, one cell per day.
Fixed layer | Lecture slots, the facility lecture, cytometer slots and the FlowJo session, journal club, the Tuesday Cutting Edge Immunology Seminar (16:30-17:30) in weeks 3 and 4, the publish-or-perish discussion, exam, poster session. Drawn by the teaching staff, dark cells, thick border, locked. Everything else is flexible.
Group rows | Plenary sessions (dark cells, bold) are mandatory. All four groups follow the same plan. Each group has its own laminar flow hood in HPL F27.2, reserved all day every day, so bench work may shift with the supervisors' agreement. Lectures and dry lab in conference room HPL F22. Nobody submits a timetable.
Checkerboard default | No checkerboard: with four hoods, all four groups do the same thing at the same time, which keeps supervision simple. Where the cytometer forces a split (week 3 Thursday), two groups acquire while the other two run the ELISA, then swap.
Core experiments | Exp 1 (week 2): polarize and characterize. Plate from the group's stock with the polarizer in the seeding suspension, vehicle and LPS controls beside it; harvest, stain, acquire; FlowJo; decide to stick or pivot before the break. Exp 2 (dry lab, weeks 2 to 4): comparison of in vitro versus in vivo polarization, see the Dry lab row. Exp 3 (week 3): polarize and challenge. Plate with the polarizer on Tuesday, challenge on Wednesday with the group's stimulus and optional inhibitor (LPS on M(-) shared by all), overnight with an IL-6 readout by default or 6 h with TNF; ELISA on Thursday. Week 4: repeat, add, or wrap up. Menus in P04 and P05. Protocol IDs (P01...) refer to protocols/ in the course repository.
Dry lab | Week 1: environment and templates. Exp 2, the in silico comparison, runs through weeks 2 to 4. Week 2: scRNA-seq part 1 (QC) in the afternoon dry-lab slots, FlowJo on the own data. Week 3: scRNA-seq part 2 (signatures from the bulk RAW 264.7 dataset) during the challenge and the ELISA incubations, own ELISA data on Friday. Week 4: scRNA-seq part 3 (scoring of the tissue macrophages), wrap up of code, figures and poster.
Rescue path | A group whose polarization or challenge failed repeats it in week 4, Tuesday 13:00 to Wednesday, as agreed with the supervisor on Friday 9 April; never at the cost of wrapping up.
Easter break | Fri 26 March to Sun 4 April. No course. The staff carry the groups' stock flasks over the break (split every 2 to 3 days, backup vials frozen on Thu 25 March).
Open items
[TODO] Cytometer: two slots of 1.5 h on Thu 25 March 09:00-12:00 (two groups each); FlowJo teaching seats for the session on Thu 25 March 13:00 (Florian Mair). Week 3 and 4 slots only through the regular booking calendar.
[TODO] Facility lecture: slot on Wed 24 March 09:00.
[TODO] FlowJo seats: number, and whether they run on student laptops or facility workstations (decides where the dry half of the day happens).
Hoods: four in HPL F27.2, one per group, reserved all day every day (settled 2026-10-28). Conference room HPL F22 reserved for lectures and dry lab.
[TODO] Supervisor names in the group row headers.
[TODO] qPCR: extension (current plan) or core.
[TODO] Course dates and Easter break: confirm with the department.
[TODO] Poster printing: printer. Deadline is Thu 15 Apr 14:00 (poster PDF committed to the group branch).

## Overview
Overview: the four weeks at a glance (default plan)
| Mon | Tue | Wed | Thu | Fri
Week 1 |  |  |  | Welcome and introductory lecture; lab and biosafety; supervisors and groups; the pathway drawing and the menu choices | Hands-on cell culture; thaw and seed the group's stock flask; git and RStudio from scratch; plan committed
Week 2 | Other lectures | Morning: other lectures. 13:00 plate with the polarizer; dry lab | Facility lecture; harvest, stain, fix | Flow acquisition; FlowJo session; journal club and debrief: stick or pivot | Good Friday
Easter | Break 26 Mar - 4 Apr; staff carry the stock flasks
Week 3 | Other lectures | Morning: other lectures. 13:00 plate with the chosen polarizer; passage the stock | Challenge (overnight IL-6 default, 6 h TNF alternative); lecture; coat ELISA plates | Harvest; ELISA with dry lab in the incubations | ELISA analysis; poster: what is missing; debrief
Week 4 | Other lectures | Morning: other lectures. 13:00 optional repeat, further experiment, or dry lab | Optional harvest and ELISA; wrap up; publish or perish | Wrap up: code, figures, poster; print when ready | Lab cleaning; finish the branch; written exam 13:00; poster session; 360° feedback; Apéro
Course days run 08:00 to 17:00, Tuesdays from 13:00; Monday and Tuesday morning are the students' other lectures. Every full day opens with a self-study hour. All four groups follow the same plan, each at its own hood; see the week sheets.
Lectures and dry lab in conference room HPL F22, bench in HPL F27.2. Cutting Edge Immunology Seminar Tue 16:30-17:30 in weeks 3 and 4.

## Week 1
Week 1: orientation (Thu 18 - Fri 19 March 2027)
Dark cells in bold are plenary and mandatory. Everything else is the default plan for all four groups; each group has its own hood all day, so bench work may shift with your supervisors' agreement. Lectures and dry lab: conference room HPL F22. Bench: HPL F27.2.
Time | Thu 18 Mar | Fri 19 Mar
08:00 | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch
09:00 | Welcome address and introductory lecture: macrophages, why they matter, why we do what we do (Joel Zindel), 09:00-10:15 | Hands-on cell culture with the staff culture: hood and sterile technique, microscope, P02 scrape, count, split and seed, cell counter. Then P01: thaw and seed your group's stock flask (course passage 0). Lab tour.
10:00
11:00 | Working in the lab and biosafety (Tea Kocijan), 10:30-12:00: Q&A, then the safety sheet is signed
12:00 | Lunch | Lunch
13:00 | Introduction of the supervisors (what they do and why) and group formation | Working with git and RStudio, step by step with the supervisors: GitHub account, install R, RStudio and Git if you did not at home, token, clone the course repository from RStudio, switch to your group's branch, open the ELISA script and run it. Then the first commit: a new text file in notebooks/ with your first notes, saved under a name you like, committed as "hello world" and pushed to your branch. Then the rest of the environment with your chatty. Group plan (the drawing and your menu choices) committed to the group branch at 17:00.
14:00 | Experiment planning with your supervisors: hand-draw the pathway you will test (ligand, receptor, output, how an inhibitor proves it, where the polarizer acts), pick your polarizer, stimulus and cytokine (P04, P05, P06) and your extension. Read P01, P02 and P08 for Friday and Tuesday.
15:00
16:00
Staff | Rooms, safety officer. Signed safety sheets collected at 12:00. Supervisors sit with their group from 14:00. | One low-passage vial per group. Supervisors carry the stock flasks over the weekend and the break: split every 2 to 3 days, course passage counted from this thaw. Afternoon: one supervisor per two laptops; the 08:00 slot is the installation help desk for latecomers. Collect the plans at 17:00.
Resources | Conference room HPL F22 for lectures and dry lab. | 4 hoods HPL F27.2, one per group, available at all times. Cell counter. Conference room HPL F22 for lectures and dry lab. Own laptops, Wi-Fi.

## Week 2
Week 2: polarize and characterize (Tue 23 - Thu 25 March 2027)
Dark cells in bold are plenary and mandatory. Everything else is the default plan for all four groups; each group has its own hood all day, so bench work may shift with your supervisors' agreement. Lectures and dry lab: conference room HPL F22. Bench: HPL F27.2.
Time | Tue 23 Mar | Wed 24 Mar | Thu 25 Mar
08:00 | Your other lectures (not course time) | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch
09:00 |  | Facility lecture: flow cytometry and FlowJo (Florian Mair) [TODO: confirm slot] | P08 Acquisition at the facility, two batches of 1.5 h, two groups each [TODO: reservation]
10:00 |  | P08 Harvest the adherent cells, count, viability dye, Fc block, surface stain
11:00
12:00 | Lunch | Lunch | Lunch
13:00 | P02 and P04: plate cells from your stock with the polarizer already in the seeding suspension. Vehicle control, M(pol) and LPS control on the flow plate (6- or 12-well). Plate-and-polarize in one step, about 19 h. Wet-lab goal: plate at a defined density with a stimulus. | P08 continued: optional Arg1 fix and perm, fix, store at 4 °C until acquisition. Wet-lab goal: harvest, staining, fixation. Staining plan and FMOs in the notebook. | FlowJo session: gating, FMOs, export statistics; the first figure [TODO: check with Florian Mair the available teaching seats]. Wet-lab goal: acquisition and gating.
14:00
15:00 | Dry lab: scRNA-seq part 1, load the preprocessed object, QC figure. If the bench runs over, the dry lab moves home. | Dry lab: scRNA-seq part 1 continued; poster: draft the introduction. If the bench runs over, the dry lab moves home.
16:00 |  |  | Journal club 1 and debrief in one session: did the polarizer do what the menu says on this readout? Stick or pivot; decision in the group branch
Staff | Stock flasks counted per group at 12:30. Polarizers, vehicle and LPS at working concentration; plate maps checked before anyone pipettes. | Antibody panel, viability dye, fix/perm buffers, compensation beads. Nothing in the incubator but the stock flasks. | Escort the groups to the facility. Stock flasks: split, two or three backup vials to -80 per group, carried over the break by the staff. Easter: no course.
Resources | 4 hoods HPL F27.2, one per group, available at all times. Cell counter. | 4 hoods HPL F27.2, one per group, available at all times. Cooled centrifuge. Fridge. Conference room HPL F22 for lectures and dry lab. | Cytometer: 2 slots of 1.5 h [TODO: facility]. Conference room HPL F22 for lectures and dry lab. FlowJo seats [TODO].

## Week 3
Week 3: polarize and challenge (Tue 6 - Fri 9 April 2027)
Dark cells in bold are plenary and mandatory. Everything else is the default plan for all four groups; each group has its own hood all day, so bench work may shift with your supervisors' agreement. Lectures and dry lab: conference room HPL F22. Bench: HPL F27.2.
Time | Tue 6 Apr | Wed 7 Apr | Thu 8 Apr | Fri 9 Apr
08:00 | Your other lectures (not course time) | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch
09:00 |  | P05 Challenge: your stimulus, optional inhibitor (TAK-242 1 h before, polymyxin B premixed), LPS on M(-) as everyone's control. Default: overnight, IL-6. Alternative: 6 h, TNF, harvest 15:00. Wet-lab goal: stimulate with inhibitor logic. | P05 Harvest (overnight groups): supernatants in aliquots, cells as RNA or protein lysate to the freezer | ELISA analysis: standard curve, concentrations. Flow statistics from week 2 in R. scRNA-seq part 2 continued.
10:00 |  |  | P06 ELISA: blocking, standards, samples; dry lab in the incubations
11:00
12:00 | Lunch | Lunch | Lunch | Lunch
13:00 | P02 and P04: plate from your stock (carried over the break) with the chosen polarizer, own approach or the standard that worked. 96-well for supernatants, extra wells for lysates. Passage the stock. | Lecture: single-cell transcriptomics for immunologists, what a signature score means (tbd) | Dry lab during the ELISA incubations: the assay waits for 3.5 h in total, which is used to prepare the next steps and for dry lab (scRNA-seq part 2). The split of wet and dry lab may shift a little. | Poster: what the story has and what it is missing; week 4 plan agreed with your supervisor (repeat, add, or wrap up)
14:00 |  | Dry lab during the challenge: scRNA-seq part 2, signatures from the bulk RAW 264.7 dataset. TNF groups: harvest at 15:00, supernatants and lysates to the freezer.
15:00 |  |  | P06 ELISA: detection and read-out; first look at the numbers. Passage the stock. Wet-lab goal: an ELISA from coating to concentration.
16:00 | Cutting Edge Immunology Seminar 16:30-17:30 (tbd) | 16:30: coat the ELISA plates with capture antibody, overnight at 4 °C (P06), 30 min at the bench |  | Debrief Exp 3: results and week 4 decisions
Staff | Stock flasks counted at 12:30. Polarizers, stimuli, inhibitors, LPS at working concentration. Plate maps checked. | Ligands, inhibitors and vehicle ready; -20 space and labelled tubes. Lysis buffers for RNA and protein. | ELISA reagents, plate reader booked. Flow on challenged cells only if a group found a slot in the regular booking. | Stock flasks: keep or freeze according to each group's week 4 plan.
Resources | 4 hoods HPL F27.2, one per group, available at all times. Plate centrifuge. | 4 hoods HPL F27.2, one per group, available at all times. Conference room HPL F22 for lectures and dry lab. | Plate reader (450 nm). 4 hoods HPL F27.2, one per group, available at all times. Conference room HPL F22 for lectures and dry lab. | Conference room HPL F22 for lectures and dry lab. 4 hoods HPL F27.2, one per group, available at all times.

## Week 4
Week 4: close the story (Tue 13 - Fri 16 April 2027)
Dark cells in bold are plenary and mandatory. Everything else is the default plan for all four groups; each group has its own hood all day, so bench work may shift with your supervisors' agreement. Lectures and dry lab: conference room HPL F22. Bench: HPL F27.2.
Time | Tue 13 Apr | Wed 14 Apr | Thu 15 Apr | Fri 16 Apr
08:00 | Your other lectures (not course time) | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch | Self-study: reading for the day, notebook, group branch
09:00 |  | Optional harvest and ELISA for groups at the bench; otherwise poster: figures and legends | Wrap up: code, figures and poster, with your supervisor. Print when ready (signprint.ch); the PDF goes to the group branch first | Lab cleaning
10:00 |  |  |  | Finish the group branch; poster pickup, self-service
11:00
12:00 | Lunch | Lunch | Lunch | Lunch
13:00 | Optional, as agreed on 9 April: repeat the polarization or the challenge, or a further experiment. Or dry lab: finish the in silico part and the poster. Never at the cost of wrapping up. | Wrap up: code, figures and poster; scRNA-seq part 3, score the tissue macrophages | Wrap up, continued: code, figures, poster, group branch. Stock flask frozen or discarded. | Written exam, individual [TODO: duration and room]
14:00 |  |  |  | Poster session: presentations and discussion; prize
15:00
16:00 | Cutting Edge Immunology Seminar 16:30-17:30 (tbd) | Publish or perish: a critical discussion on scientific integrity and output metrics |  | Open 360° feedback round: closes the poster session and opens the apéro
Staff | Reagents for the agreed repeats or extensions. Stock flasks for the groups that plate. | Poster template distributed. Plate reader for the groups that ran an ELISA. | Poster boards ready. Exam papers printed. Course evaluation goes out as a written survey. | Exam papers, jury, prize, clean-up checklist. Apéro ordered [TODO: catering]; evaluation survey sent after the course.
Resources | 4 hoods HPL F27.2, one per group, available at all times. Extension-specific instruments as agreed. Conference room HPL F22 for lectures and dry lab. | 4 hoods HPL F27.2, one per group, available at all times. Conference room HPL F22 for lectures and dry lab. | Conference room HPL F22 for lectures and dry lab. Poster boards. | Conference room HPL F22 for lectures and dry lab. Apéro room [TODO: catering].